## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2208-SWEN-261-01-2-Fanta
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | JZ; 06/27/2021 | Pass | JZ; 07/14/2021
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | JZ; 06/27/2021 | Pass | JZ; 07/14/2021
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | DK; 06/27/2021; This initial acceptance criteria was not met because you could not use numeric character. DK; 06/27/2021; This has been fixed. | Pass | JZ; 07/14/2021
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | JZ; 06/27/2021; Initial acceptance criteria was not originally met due to not accepting numeric characters. JZ; 06/27/2021; This has been resolved | Pass | JZ; 07/14/2021
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | DK; 06/27/2021 | Pass | JZ; 07/14/2021
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | JZ; 06/27/2021 | Pass | JZ; 07/14/2021
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | DK; 06/27/2021 | Pass | JZ; 07/14/2021
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | JZ; 06/27/2021 | Pass | JZ; 07/14/2021
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | JZ; 06/27/2021 | Pass | JZ; 07/14/2021
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | DK; 06/27/2021 | Pass | JZ; 07/14/2021
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | DK; 06/27/2021 | Pass | JZ; 07/14/2021
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | JZ; 06/27/2021 | Pass | JZ; 07/14/2021
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | DK; 06/27/2021 | Pass | JZ; 07/14/2021
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | DK; 06/27/2021; Unsure if the ajax call results in failure DK; 06/28/2021; Ajax call was confirmed by Bobby to make sense. | Pass | JZ; 07/14/2021
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | JZ; 06/27/2021 | Pass | JZ; 07/14/2021
As a Player who is logged in I want to have an option to log out so that I can stop playing checkers. | Given I am signed in when I click the sign out button then I expect to be signed out. |  |  | Pass | DK; 07/11/2021
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) |  |  | Pass | DK; 07/11/2021
| Given that I am in a game when I see the Game page then I must not be able to sign out. |  |  | Pass | DK; 07/11/2021; Currently there is a sign out link on the game page.; DK; 07/11/2021; On the sprint 2 info page, there IS a sign out link, however you cannot sign out during the game, thus the acceptance criteria has been corrected.; DK; 07/11/2021; Now you cannot sign out while playing the game, however clicking the link that exists there can cause a problem where neither player is allowed to move pieces.; DK; 07/11/2021; All issues fixed.
| Given that I have signed out when a player tries to sign in then they must be able to sign in with the name I was using before I signed out. |  |  | Pass | DK; 07/11/2021
| Given that I have not signed in when I see the Home page then I must not see a means to sign-out. |  |  | Pass | DK; 07/11/2021
As a Player I want to be forced to move one of my checkers on my turn so I can play American checkers correctly. | Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  |  | Pass | DK; 07/11/2021
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  |  | Pass | DK; 07/11/2021
| Given a valid, initial game board when I drag a piece to a non occupied black space that is not away from the player then the piece should not be droppable. |  |  | Pass | DK; 07/11/2021
| Given a valid, initial game board when I drag a piece to a non occupied black space that is not diagonally adjacent from the player then the piece should not be droppable. |  |  | Pass | DK; 07/11/2021
As a player I want to be forced to jump over my opponent’s checker if possible so that I can capture my opponent’s checker. | Given that my checker is diagonally adjacent to an unoccupied dark square, with my opponents checker occupying a diagonal space between them when I try to place the checker on the square on the other side of the opponent's checker then the piece should be droppable |  |  | Pass | EL; 07/11/2021
| Given that my checker is diagonally adjacent to the opponent's checker with an open space behind it when I try to put my checker on a space directly diagonally adjacent to the piece then the checker should not be droppable. |  |  | Pass | EL; 07/11/2021
| Given that my opponent's checker is diagonally adjacent to one of my checkers and has a diagonally open space behind it when I try to move a checker that isn't the one in position to make a jump move then the piece should not be droppable. |  |  | Pass | EL; 07/11/2021
As a player when I jump over an opponent’s checker I want it to disappear from the board so that I can capture my opponent’s checker. | Given that a jump move is available whe I perform the jump move then the opponent piece that I jump over is captured and removed from the board |  |  | Pass | DK; 07/11/2021
| Given that one of my pieces lies diagonally between my piece and an unoccupied valid space, when I attempt a jump move then that move is not valid and I cannot perform it |  |  | Pass | EL; 07/11/2021
As a player with multiple possible jumps I want to be able to choose which jump to make so that I can play strategically. | Given multiple jump moves are possible for any of my pieces when it is my turn then I want to see the possible jump moves |  |  | Pass | DK; 07/11/2021
| Given that I have chosen a jump move from the available possibilities for my pieces when I select that move then that move is performed |  |  | Pass | DK; 07/11/2021
| Given that there are no jump moves available when it is my turn then I must make a normal move |  |  | Pass | DK; 07/11/2021
As a player immediately after jumping over an opponent’s checker I want to be forced to jump over my opponent’s next checker if possible so that I can do multiple jumps in a single move. | Given a jump move is still possible when I have completed a jump move already then I am forced to perform that jump move |  |  | Pass | DK; 07/11/2021
| Given that I have performed a jump move, when I am forced to perform a multiple jump move then my turn does not end until the multiple jump move is completed |  |  | Pass | DK; 07/11/2021
As a player I want to king my normal checker when it reaches the far end of the checkerboard so that I get a kinged checker. | Given I have a piece that is one move away from reaching the far end of the board when I perform that move then that piece becomes a 'king' |  |  | Pass | DK; 07/11/2021
As a player, I want to be able to move my kinged checkers one space diagonally in any direction so that I can play checkers correctly. | Given I have a king checker when I move it then I expect it to be able to move one square in any diagonal direction. |  |  | Pass | DK; 07/11/2021
| Given I have a king checker when I try to jump over an opponents checker it then I expect it to be able to move jump in any diagonal direction. |  |  | Pass | DK; 07/11/2021
| Given a valid, game board when I drag a king piece to a non occupied black space that is not diagonally adjacent to the piece then the piece should not be droppable. |  |  | Pass | DK; 07/11/2021
| Given a valid, game board and that it is my turn when I drag a king piece to a non occupied black space that is diagonally adjacent to the king I am moving then the king should be droppable. |  |  | Pass | DK; 07/11/2021
| Given I have a king checker when I try to jump over an empty square then I expect it to not be able to jump. |  |  | Pass | DK; 07/11/2021